## Estimate Summary
Single Family Home New Build Estimate
Client | Martinez Family |  | Cost Category | Amount
Location | Frisco, TX |  | Material Total | 431246.5
Estimator | Sample Estimator |  | Labor Total | 237202.48
Estimate Date | 2026-05-20 |  | Equipment Total | 16614.7
Planned Start | 2026-07-01 |  | Direct Cost | 685063.68
Duration Days | 165 |  | Contingency | 54805.0944
Markup % | 15% |  | Markup | 102759.552
Contingency % | 8% |  | Grand Total | 842628.3264
Division | Direct Cost | % of Direct | Estimated Total
Site | 15836.48 | 2.312% | 19478.8704
Concrete | 87840 | 12.82% | 108043.2
Framing | 126191.8 | 18.42% | 155215.914
Exterior | 87754.6 | 12.81% | 107938.158
MEP | 133136 | 19.43% | 163757.28
Interior | 214694.8 | 31.34% | 264074.604
Final | 19610 | 2.863% | 24120.3

## Detailed Estimate
Division | Description | Unit | Qty | Material Unit Cost | Labor Hours/Unit | Labor Rate | Equipment Unit Cost | Material Total | Labor Total | Equipment Total | Direct Cost | Contingency | Markup | Estimated Total | Status | Notes
Site | Temporary utilities and fencing | LS | 1 | 6200 | 20 | 45 | 1200 | 6200 | 900 | 1200 | 8300 | 664 | 1245 | 10209 | In Scope | Sample quantity and rate for estimator use
Site | Clearing and grading | AC | 0.42 | 14500 | 18 | 58 | 2400 | 6090 | 438.48 | 1008 | 7536.48 | 602.9184 | 1130.472 | 9269.8704 | In Scope | Sample quantity and rate for estimator use
Concrete | Foundation slab | SF | 3220 | 9.85 | 0.16 | 60 | 0.75 | 31717 | 30912 | 2415 | 65044 | 5203.52 | 9756.6 | 80004.12 | In Scope | Sample quantity and rate for estimator use
Concrete | Driveway and flatwork | SF | 1640 | 7.9 | 0.1 | 54 | 0.6 | 12956 | 8856 | 984 | 22796 | 1823.68 | 3419.4 | 28039.08 | In Scope | Sample quantity and rate for estimator use
Framing | Lumber package | SF | 3220 | 18.75 | 0.22 | 52 | 0.55 | 60375 | 36836.8 | 1771 | 98982.8 | 7918.624 | 14847.42 | 121748.844 | In Scope | Sample quantity and rate for estimator use
Framing | Roof trusses | SF | 3220 | 5.65 | 0.05 | 52 | 0.2 | 18193 | 8372 | 644 | 27209 | 2176.72 | 4081.35 | 33467.07 | Sub Quote | Sample quantity and rate for estimator use
Exterior | Roofing shingles | SQ | 38 | 385 | 5.5 | 49 | 25 | 14630 | 10241 | 950 | 25821 | 2065.68 | 3873.15 | 31759.83 | In Scope | Sample quantity and rate for estimator use
Exterior | Windows | EA | 31 | 525 | 1.1 | 56 | 12 | 16275 | 1909.6 | 372 | 18556.6 | 1484.528 | 2783.49 | 22824.618 | In Scope | Sample quantity and rate for estimator use
Exterior | Brick veneer | SF | 2850 | 8.75 | 0.12 | 51 | 0.35 | 24937.5 | 17442 | 997.5 | 43377 | 3470.16 | 6506.55 | 53353.71 | Allowance | Sample quantity and rate for estimator use
MEP | Plumbing rough and trim | LS | 1 | 39200 | 110 | 69 | 1800 | 39200 | 7590 | 1800 | 48590 | 3887.2 | 7288.5 | 59765.7 | Sub Quote | Sample quantity and rate for estimator use
MEP | Electrical rough and trim | LS | 1 | 44500 | 128 | 67 | 1500 | 44500 | 8576 | 1500 | 54576 | 4366.08 | 8186.4 | 67128.48 | Sub Quote | Sample quantity and rate for estimator use
MEP | HVAC system | TON | 5 | 5200 | 9 | 66 | 200 | 26000 | 2970 | 1000 | 29970 | 2397.6 | 4495.5 | 36863.1 | Sub Quote | Sample quantity and rate for estimator use
Interior | Insulation | SF | 8800 | 1.25 | 0.04 | 43 | 0.02 | 11000 | 15136 | 176 | 26312 | 2104.96 | 3946.8 | 32363.76 | In Scope | Sample quantity and rate for estimator use
Interior | Drywall hang and finish | SF | 12800 | 2.25 | 0.08 | 46 | 0.02 | 28800 | 47104 | 256 | 76160 | 6092.8 | 11424 | 93676.8 | In Scope | Sample quantity and rate for estimator use
Interior | Cabinetry | LF | 86 | 425 | 0.65 | 58 | 8 | 36550 | 3242.2 | 688 | 40480.2 | 3238.416 | 6072.03 | 49790.646 | Allowance | Sample quantity and rate for estimator use
Interior | Flooring mixed package | SF | 2980 | 6.85 | 0.07 | 44 | 0.04 | 20413 | 9178.4 | 119.2 | 29710.6 | 2376.848 | 4456.59 | 36544.038 | Allowance | Sample quantity and rate for estimator use
Interior | Paint interior | SF | 14200 | 1.05 | 0.045 | 42 | 0.02 | 14910 | 26838 | 284 | 42032 | 3362.56 | 6304.8 | 51699.36 | In Scope | Sample quantity and rate for estimator use
Final | Appliance package | LS | 1 | 18500 | 12 | 55 | 450 | 18500 | 660 | 450 | 19610 | 1568.8 | 2941.5 | 24120.3 | Allowance | Sample quantity and rate for estimator use

## Rates & Assumptions
Single Family Home New Build Estimate - Rates & Assumptions
Project Name | Single Family Home New Build Estimate
Client | Martinez Family
Location | Frisco, TX
Estimator | Sample Estimator
Estimate Date | 46162
Planned Start | 46204
Duration Calendar Days | 165
Estimate Class | Budget / Design Development
Markup % | 15%
Contingency % | 8%
Sales Tax % | 8.25%
Labor Burden % | 28%
Default Crew Productivity | Project-specific
Bid Validity Days | 30
Currency | USD

## Vendor Quotes
Vendor/Subcontractor | Scope | Quoted Amount | Status | Date Received | Estimator Notes
Premier Plumbing | Full plumbing scope | 39200 | Received | 2026-06-18 | Compare inclusions, exclusions, tax, bonding, and schedule constraints.
DFW Electrical Pros | Electrical rough and trim | 44500 | Received | 2026-06-19 | Compare inclusions, exclusions, tax, bonding, and schedule constraints.
Comfort Air | 5-ton HVAC system | 26000 | Pending | 2026-06-21 | Compare inclusions, exclusions, tax, bonding, and schedule constraints.
North Star Cabinets | Kitchen and bath cabinetry | 36550 | Budget | 2026-06-15 | Compare inclusions, exclusions, tax, bonding, and schedule constraints.

## Scope Notes
Single Family Home New Build Estimate - Scope Notes
Item | Included / Excluded | Description | Risk Level | Owner | Due Date
Basis of Estimate | Included | Sample estimate created for project pricing practice and estimator workflow. | Medium | Estimator | 2026-05-24
Plans and Specs | Included | Quantities are based on assumed preliminary takeoff data. Verify against final drawings. | High | Estimator | 2026-05-28
Permit Fees | Included | Permit allowance included unless specifically noted by line item. | Medium | PM | 2026-06-01
Utility Company Fees | Excluded | Direct utility fees are excluded unless vendor quote states otherwise. | High | Owner | 2026-06-05
Overtime Work | Excluded | Assumes normal working hours and standard sequencing. | Medium | PM | 2026-06-08
Tax and Markup | Included | Rates are controlled by the Rates & Assumptions sheet. | Low | Estimator | 2026-05-22

## Lists
Status | Quote Status
In Scope | Received
Allowance | Pending
Sub Quote | Budget
Excluded | Rejected
Pending | Need Clarification
Budget