## Estimate Summary
PROJECT ESTIMATE SUMMARY
Project Name | Sample Commercial Build-Out | Category | Direct Cost | % of Direct Cost
Location | Lubbock, TX | General Conditions | 59790 | 6.826%
Estimate Date | 2026-05-20 | Sitework | 56400 | 6.439%
Bid Due Date | 2026-06-10 | Concrete | 51218 | 5.847%
Gross Area (SF) | 12500 | Structural Steel | 86300 | 9.853%
Duration (Weeks) | 18 | Carpentry | 6336 | 0.7234%
Total Bid | 1066810.341 | Roofing | 59800 | 6.827%
Cost / SF | 85.3448 | Openings | 43672 | 4.986%
|  | Finishes | 160295 | 18.3%
Summary Item | Amount | MEP | 352100 | 40.2%
Direct Cost Subtotal | 875911 | Contingency | 0 | 0%
Material Tax | 7455.525
Insurance / Bond | 13138.665
Small Tools | 1483.3125 | Status | Line Count | Direct Cost | Average Line Cost | Notes
Subtotal Before OH&P | 897988.5025 | Pending | 5 | 128270 | 25654 | Needs follow-up
Overhead | 71839.0802 | Quoted | 10 | 637850 | 63785 | Vendor quote received
Profit | 96982.7583 | Approved | 5 | 109791 | 21958.2 | Ready for bid
Total Bid | 1066810.341 | Change Order | 0 | 0 | 0 | Separate tracking
|  | Excluded | 0 | 0 | 0 | Not in bid

## Estimate Details
DETAILED PROJECT ESTIMATE
WBS | Category | Description | Status | Cost Type | Quantity | Unit | Unit Cost | Labor Hrs | Labor Rate | Material Cost | Equipment Cost | Subcontract Cost | Line Total | Notes
01-001 | General Conditions | Mobilization and project setup | Approved | Other | 1 | LS | 7500 | 0 | 0 | 0 | 0 | 0 | 7500 | Temporary setup and closeout
01-002 | General Conditions | Superintendent weekly oversight | Approved | Labor | 18 | WK | 0 | 720 | 62 | 0 | 0 | 0 | 44640 | 40 hrs/week
01-003 | General Conditions | Temporary facilities and utilities | Quoted | Other | 18 | WK | 425 | 0 | 0 | 0 | 0 | 0 | 7650 | Trailer, toilet, temp power
02-001 | Sitework | Site clearing and rough grading | Quoted | Subcontractor | 1 | LS | 0 | 0 | 0 | 0 | 0 | 18500 | 18500 | Allowance quote
02-002 | Sitework | Dumpster and haul-off allowance | Pending | Other | 6 | EA | 900 | 0 | 0 | 0 | 0 | 0 | 5400 | Construction waste
03-001 | Concrete | Concrete slab on grade | Quoted | Subcontractor | 12500 | SF | 0 | 0 | 0 | 0 | 0 | 47250 | 47250 | Vendor quote
03-002 | Concrete | Anchor bolts and embedded plates | Pending | Material | 1 | LS | 3200 | 16 | 48 | 0 | 0 | 0 | 3968 | Coordinate with steel
05-001 | Structural Steel | Steel material and erection | Quoted | Subcontractor | 42 | TON | 0 | 0 | 0 | 0 | 0 | 86300 | 86300 | Vendor quote
06-001 | Carpentry | Rough carpentry blocking | Approved | Labor | 1 | LS | 2400 | 72 | 38 | 1200 | 0 | 0 | 6336 | Blocking at doors and millwork
07-001 | Roofing | TPO roof system | Quoted | Subcontractor | 12800 | SF | 0 | 0 | 0 | 0 | 0 | 59800 | 59800 | Vendor quote
08-001 | Openings | Doors, frames, and hardware | Pending | Material | 28 | EA | 1450 | 64 | 48 | 0 | 0 | 0 | 43672 | Includes install labor
09-001 | Finishes | Metal studs and drywall partitions | Approved | Labor | 12500 | SF | 2.95 | 380 | 38 | 0 | 0 | 0 | 51315 | Interior partitions
09-002 | Finishes | ACT ceiling grid and tile | Pending | Material | 8600 | SF | 4.35 | 140 | 38 | 0 | 0 | 0 | 42730 | Installed ceiling
09-003 | Finishes | Flooring package | Quoted | Subcontractor | 12500 | SF | 0 | 0 | 0 | 0 | 0 | 38800 | 38800 | Vendor quote
09-004 | Finishes | Painting package | Quoted | Subcontractor | 12500 | SF | 0 | 0 | 0 | 0 | 0 | 27450 | 27450 | Vendor quote
22-001 | MEP | Plumbing rough-in and fixtures | Quoted | Subcontractor | 1 | LS | 0 | 0 | 0 | 0 | 0 | 74200 | 74200 | Vendor quote
23-001 | MEP | HVAC equipment and ductwork | Quoted | Subcontractor | 1 | LS | 0 | 0 | 0 | 0 | 0 | 149500 | 149500 | Vendor quote
26-001 | MEP | Electrical power and lighting | Quoted | Subcontractor | 1 | LS | 0 | 0 | 0 | 0 | 0 | 128400 | 128400 | Vendor quote
32-001 | Sitework | Paving and striping allowance | Pending | Subcontractor | 1 | LS | 0 | 0 | 0 | 0 | 0 | 32500 | 32500 | Placeholder allowance
99-001 | Contingency | Estimator contingency allowance | Approved | Other | 1 | Allowance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Calculated on summary

## Rates & Assumptions
PROJECT ESTIMATOR RATES & ASSUMPTIONS
Project Name | Sample Commercial Build-Out |  | Labor Role | Base Rate / Hr | Burden %
Location | Lubbock, TX |  | Project Manager | 68 | 30%
Estimator | Estimator Name |  | Superintendent | 62 | 28%
Estimate Date | 46162 |  | Foreman | 48 | 25%
Bid Due Date | 46183 |  | Carpenter | 38 | 22%
Gross Area (SF) | 1250000% |  | Laborer | 28 | 20%
Construction Duration (Weeks) | 1800% |  | Electrician | 52 | 26%
Overhead % | 8% |  | Plumber | 55 | 26%
Profit % | 0.1 |  | HVAC Tech | 54 | 26%
Contingency % | 0.05
Markup Basis | Formula / Use | Value | Notes
Material Tax | Applied to taxable materials only | 8.25% | Adjust per project location
Insurance/Bond | Applied to subtotal before OH&P | 1.5% | Typical placeholder
Small Tools | Applied to direct labor | 2.5% | Field consumables
Waste Factor | Applied selectively by item | 10% | Use for drywall, flooring, framing
Escalation | Applied if quote expires before bid | 3% | Optional

## Vendors
VENDOR / SUBCONTRACTOR QUOTE LOG
Trade | Company | Contact | Phone | Email | Quote Date | Quote Amount | Notes
Concrete | West Plains Concrete | Maria Lopez | 806-555-0112 | mlopez@example.com | 2026-05-12 | 47250 | Includes slab and footings
Structural Steel | Caprock Steel Supply | Daniel Reed | 806-555-0181 | dreed@example.com | 2026-05-13 | 86300 | Excludes embed coordination
Roofing | High Plains Roofing | Steven Clark | 806-555-0177 | sclark@example.com | 2026-05-15 | 59800 | TPO roof allowance
Electrical | Red Raider Electric | Priya Shah | 806-555-0133 | pshah@example.com | 2026-05-16 | 128400 | Lighting package included
Plumbing | Hub City Plumbing | John Miller | 806-555-0166 | jmiller@example.com | 2026-05-16 | 74200 | Fixture allowance included
HVAC | South Plains Mechanical | Emily Carter | 806-555-0150 | ecarter@example.com | 2026-05-17 | 149500 | RTUs and ductwork
Flooring | Llano Flooring Co. | Ahmed Khan | 806-555-0199 | akhan@example.com | 2026-05-18 | 38800 | LVT and carpet tile
Painting | Prairie Paintworks | Chris Young | 806-555-0144 | cyoung@example.com | 2026-05-18 | 27450 | Walls, frames, and doors

## Project Scope
PROJECT SCOPE / QUANTITY TAKEOFF NOTES
Area / System | Scope Description | Quantity | Unit | Drawing Ref | In Estimate? | Notes
Site | Mobilization, temporary fencing, dumpsters | 1 | LS | C-001 | Yes | General project setup
Foundations | Concrete slab, grade beams, vapor barrier | 12500 | SF | S-101 | Yes | Based on conceptual plan
Shell | Structural steel framing and decking | 42 | TON | S-201 | Yes | Includes erection
Roof | TPO roofing system | 12800 | SF | A-301 | Yes | Includes insulation
Interior | Metal studs, drywall, acoustical ceilings | 12500 | SF | A-601 | Yes | Tenant build-out
Openings | Hollow metal doors, frames, hardware | 28 | EA | A-701 | Yes | Door schedule basis
Finishes | Flooring, paint, wall base | 12500 | SF | A-801 | Yes | Allowance level pricing
MEP | Electrical, plumbing, HVAC systems | 12500 | SF | M/E/P | Yes | Subcontractor quotes
Exclusions | Permits, utility tap fees, owner furniture | 1 | LS | N/A | No | Excluded unless added by owner

## Lists
Status | Category | Unit | Cost Type
Pending | Sitework | LS | Material
Quoted | Concrete | EA | Labor
Approved | Masonry | SF | Equipment
Change Order | Structural Steel | SY | Subcontractor
Excluded | Carpentry | LF | Other
| Roofing | CY
| Openings | TON
| Finishes | HR
| MEP | DAY
| General Conditions | WK
| Contingency | MO
Allowance
Lot